## Issues 1
EXPERTCAGE ISSUES
S/N | SECTION | ISSUE | ATTENDED TO? | Comment(s) | Assigned to or solved by?
| Contact Form | Mails Not Delivered and yet shows error msg after sending. Let's use support@expertcage.com | NO |  | NONE
| LOGIN | Recovery of Password not working | NO |  | NONE
| footer Links | all social icons donot link to the right pages | NO |  | NONE
| FAQ | only one question is there, we need to have a variety of questions | NO |  | NONE
| PAYMENTS | we need provide other alternatives to the payment means like Mobile Money | NO |  | NONE
| Sign ups |  | NO |  | NONE
| as a client | after successfully creatin account, the login link should be provided to the user | NO |  | NONE
| login as expert | quiz form not working, so you cant proceed | NO |  | NONE
| Login Pge | forgot password does not work after providing the email for a recovery. we need to sort it | NO |  | NONE
| AS A CLIENT (Dashboard) |  | NO |  | NONE
| side bar | account does not have satisfying information about the client | NO |  | NONE
|  | current project, i suggest that the drop down should display project names not project numbers | NO |  | NONE
|  | previous project, clicking on the details of a project, and go to attachments, you can not open an attachment neither download it | NO |  | NONE
|  | placing X on both messages and attachments does not delete the attachment.it just hides it. i suggest it deletes it | NO |  | NONE
|  | the post time and deadline time needs to be sorted does not pick the correct time | NO |  | NONE
|  | my profile: i feel much more information is missing | NO |  | NONE
|  | Payment statistics: not working | NO |  | NONE
|  | Depost money: on the top bar does not work. needs to be sorted | NO |  | NONE
|  | Search on top doesnot work needs to be sorted | NO |  | NONE
| ADMIN SIDE |  | NO |  | NONE
| dashboard | payment statisics not working yet | NO |  | NONE
|  | Make payments not working | NO |  | NONE
|  | projects in progress shows 10. this value not true | NO |  | NONE
|  | new projects shows 0 yet there are some projects | NO |  | NONE
|  | wen you go to "Applicants", Account status is not working | NO |  | NONE
|  | Others Not working at all including categories, academic levels and payments | NO |  | NONE
|  |  | NO |  | NONE
|  |  | NO |  | NONE
|  |  | NO |  | NONE
|  |  | NO |  | NONE
|  |  | NO |  | NONE
|  |  | NO |  | NONE
|  |  | NO |  | NONE
|  |  | NO |  | NONE
|  |  | NO |  | NONE
|  |  | NO |  | NONE
|  |  | NO |  | NONE
|  |  | NO |  | NONE
|  |  | NO |  | NONE

## External Audit
EXPERTCAGE EXTERNAL AUDIT
S/N | SECTION | ISSUE | Comment(s)
1 | Signup | password strengh is week. it should require special characters and characters should be atleast 6
| Social Link icons | all social icons donot link to the right pages